## Cover
Transaction Monitoring Onboarding Sheet |  |  |  | Help Centre | Notes
Over on this side you can find helpful tips and advice when completing the workbook.
Details | [5 empty] | Please work your way through the workbook in the order shown. This is to adhere to the natural flow of the implementation process.
Client
Kickoff Date |  |  |  |  | Guide
Target Go Live Date |  |  |  |  | 1 | All cells with a blue background are for the sole use of ComplyAdvantage
ComplyAdvantage PM |  |  |  |  | 2 | Example Data is marked in light grey. Please delete or use where appropriate, changing the text colour to black.
Client PM
Client Project Sponsor
Client Tech
Client Compliance
Versions
# | Date | User | Description
1
2
3
4
5
6
7
8

## Project Plan - Onboarding
Project Plan - Onboarding
Description | This project plan should be used when a client is first set up on the TM platform.
|  |  | Planned |  |  | Actual
Phase | Deliverables | Who | Duration (UK workdays) | Start Date | End Date | Start Date | End Date | Duration (UK workdays) | Status | Schedule Variation - Stage | Schedule Variation - Cumulative
Kick-off | [8 empty] | Not Started
| Kick-off call | ComplyAdvantage PM | 1 | 2021-06-16 | 2021-06-16 |  |  |  | Not Started
Scoping | [8 empty] | Not Started
| Initial Rules & Data-model submitted | Client Compliance | 5 | 2021-06-17 | 2021-06-23 |  |  |  | Not Started
| CA review | ComplyAdvantage PM | 5 | 2021-06-24 | 2021-06-30 |  |  |  | Not Started
| Outstanding questions resolved (rules, source format, workflow) | ComplyAdvantage PM
Build | [8 empty] | Not Started
| QA environment build | ComplyAdvantage PM | 10 | 2021-07-01 | 2021-07-14 |  |  |  | Not Started
| CA testing | ComplyAdvantage PM | 5 | 2021-07-15 | 2021-07-21 |  |  |  | Not Started
UAT | [8 empty] | Not Started
| Client training | ComplyAdvantage PM | 1 | 2021-07-22 | 2021-07-22 |  |  |  | Not Started
| Rule, UI, Workflow and User testing | Client Compliance | 5 | 2021-07-23 | 2021-07-29 |  |  |  | Not Started
| API integration and testing | Client Tech
| Outstanding questions resolved | ComplyAdvantage PM | 5 | 2021-07-30 | 2021-08-05 |  |  |  | Not Started
Move to Prod | [8 empty] | In Progress
| Migrate to production | ComplyAdvantage PM | 1 | 2021-08-06 | 2021-08-06 |  |  |  | Not Started
| Add users to production environment | ComplyAdvantage PM
Formulas:
End Date = if(ISBLANK([Start Date]),"",WORKDAY([Start Date],[Duration (UK workdays)]-1,Config!J7:J21))
End Date = if([Start Date]="","",WORKDAY([Start Date],[Duration (UK workdays)]-1,Config!J7:J21))
Duration (UK workdays) = if(isblank([Start Date]),"",if(isblank([End Date]),"",NETWORKDAYS([Start Date],[End Date],Config!J7:J21)))
Duration (UK workdays) = if(isblank([Start Date]),"",if(isblank([End Date]),"",NETWORKDAYS([Start Date],[End Date],Config!J7:[End Date, row below])))
Status = if(isblank([Start Date]),"Not Started", if([Start Date]<=TODAY(),if(isblank([End Date]),"In Progress",if([End Date]<TODAY(),"Completed","In Progress")),"Not Started"))
Schedule Variation - Cumulative = if([Duration (UK workdays)] = "","",if([End Date]=[End Date],0,if([End Date]>[End Date], NETWORKDAYS([End Date],[End Date],Config!$J7:J21)-1,NETWORKDAYS([End Date],[End Date],Config!$J7:J21)+1)))
Start Date = if([End Date, row above]="","",WORKDAY([End Date, row above],1,Config!J7:J21))
Start Date = if(H20="","",WORKDAY(H20,1,Config!J7:[End Date, row below]))

## 1.1 Client Details
Client Details
Industry
Annual Tx Volume |  | The transaction monitoring system can handle various sources of data, each of which may have their own formats/structure. Please list here the various data sources you may require. One source format is preferable. Source formats are separate data structures and have separate rule sets. We advise one upload style per source format. If a client has multiple source formats, they can use different upload styles for each source format if required. If a client requires multiple upload styles on a single source format, please discuss with SEs.
Region
Screening
Entity Name Screening
Ref Text Name Screening
Ref Text Risk Word Screening
Upload Style
Webhooks
Source Formats
Name | Description
Entities
Name | Description | Help
Customer | Party who has an account with you. | A single transaction can contain two or more entities within it. Please list here the various entities.
Counterparty | Party your customer is transacting with.

## 1.2 Initial Questionnaire
Initial Questionnaire
Question | Answer
Client Business/Internal Process
Do you have multiple business units? Are these units separate?
What does your current remediation workflow look like?
Products
What different products do you offer? | online app both web and mobile and people living in canada can send money to families in india. only candadians can sign up for the app. can only send money to india - in the future will expand. Can add money by e-transfer, debit, no cash. every account has to have unique mobile number. No internal transfers. beneficiaries have an external account/
Can your products be used to both send and receive money?
Can your customers use more than one of your products? If so, will they have separate accounts for each product attached to the same customer ID?
If customers can use multiple products, do you need to monitor their behaviour across products, or do you need to monitor behaviour separately per product? (Note: this can be different per rule)
Do these products have different monitoring requirements? (e.g. different rules needed, different limits needed)
Do you have different data available for different products?
Transaction Types
What different transaction types do you have? (this should also include any non-monetary transactions you need monitored in rules, such as account changes)
If you have different products, are transaction types different for those products?
Do these transaction types have different monitoring requirements? (e.g. different rules needed, different limits needed)
Do you have different data available for different transaction types?
Entities
How many parties can be involved in your transactions? Do each of these parties have a unique identifier? (this should include all possible parties, even if they are not involved in every transaction) | unique ID for beneficiaries
Do your customers make internal (to other customer/to themselves/to you) or external (parties external to your business) transactions or both?
If your customer makes internal transactions, will their customer ID be the same whether they are sending or receiving the transaction?
Are all parties involved in all transactions? Or are they specific to products or transaction types?
Regulations/Risks
What regulations are you required to met?
What risks do you need to consider?
Multiple Source Formats Questionnaire
Question | Answer
What will determine which source format a transaction is on?
Will the source formats have different data models?
Can an entity have transactions in multiple source formats? If so, will their unique identifier be the same in all source format?
Would a transaction in one source format need to consider a transaction in another source format? (Note: this is not possible on the system, so if the answer is yes, please consolidate source formats)
Screening Questionnaire
Question | Answer
Can you provide unique identifiers for every entity you intend to use name screening on?
Are the entities you intend to use name screening on involved in all transactions?
Do you need to use joint account screening on any of the entities you intend to use name screening on?

## 2. Data Model
Help
|  | Data Model | [13 empty] | Please create a new sheet for each of the source formats listed, renaming each sheet to include the source format name (i.e. '2. Data Model - ACH').
Source Format
UI Visibilty
# | CA NAME | <<Client Name>> | Description | Type | Format | Possible Values | Unique Id? | Required? | Used in a rule | Transaction View | Entity View | Alert View | Linked Transactions Filter | Filterable on Transaction Summary?
Transaction information
1 | tx_id |  | Transaction unique identifier | StringType |  |  | YES | true | NO |  | N/A
2 | tx_date_time |  | Datetime transaction created at | DateTimeType | YYYY-MM-DD HH:MM:SS |  | NO | true | NO |  | N/A
3 | tx_direction |  | Transaction's direction | StringType |  | Inbound/Outbound/... | NO | true | YES |  | N/A
4 | tx_type |  | Transaction type | StringType |  | Third Party Transaction | NO | false | NO |  | N/A
5 | tx_base_currency |  | Operating (base) currency | StringType |  |  | NO | true | NO |  | N/A
6 | tx_base_amount | CAD | Amount in operating (base) currency | DecimalType |  |  | NO | true | YES |  | N/A
7 | tx_currency |  | Actual currency | StringType |  |  | NO | false | NO |  | N/A
8 | tx_amount | AUD, GBP, CAD, INR | Amount in actual currency | DecimalType |  |  | NO | false | NO |  | N/A
9 | tx_reference_text |  | Transaction reference text | StringType |  |  | NO | false | NO |  | N/A
10 | tx_product |  |  | StringType |  |  | NO | false | NO |  | N/A
11 | tx_payment_channel |  |  | StringType |  |  | NO | false | NO |  | N/A
12 | tx_mcc_code |  |  | StringType |  |  | NO | false | NO |  | N/A
13 | tx_loan_funding_datetime |  |  | DateTimeType | YYYY-MM-DD HH:MM:SS |  | NO | false | NO |  | N/A
14 | tx_loan_settlement_datetime |  |  | DateTimeType | YYYY-MM-DD HH:MM:SS |  | NO | false | NO |  | N/A
15 | tx_loan_expected_repayment_datetime |  |  | DateTimeType | YYYY-MM-DD |  | NO | false | NO |  | N/A
16 | tx_loan_monthy_expected_installment_amount |  |  | DecimalType |  |  | NO | false | NO |  | N/A
17 | tx_calendar_year |  |  | StringType |  |  | NO | false | NO |  | N/A
18 | tx_calendar_month |  |  | StringType |  |  | NO | false | NO |  | N/A
Customer information
19 | customer_id | Pay penny customer number | Customer unique identifier | StringType |  |  | YES | true | YES |  | Customer
20 | customer_name |  | Customer name | StringType |  |  | YES | true | NO |  | Customer
21 | customer_type |  | Customer type | StringType |  |  | YES | false | NO |  | Customer
22 | customer_account_balance |  |  | DecimalType |  |  | NO | false | NO |  | Customer
23 | customer_account_currency |  |  | StringType |  |  | NO | false | NO |  | Customer
24 | customer_base_account_balance |  |  | DecimalType |  |  | NO | false | NO |  | Customer
25 | customer_account_number |  |  | StringType |  |  | NO | false | NO |  | Customer
26 | customer_account_type |  |  | StringType |  |  | NO | false | NO |  | Customer
27 | customer_sort_code |  |  | StringType |  |  | NO | false | NO |  | Customer
28 | customer_risk_category |  | customer risk level | StringType |  | Low/Medium/High | NO | false | NO |  | Customer
29 | customer_date_of_birth |  |  | DateTimeType | YYYY-MM-DD |  | NO | false | NO |  | Customer
30 | customer_country |  |  | StringType |  |  | NO | false | NO |  | Customer
31 | customer_state |  |  | StringType |  |  | NO | false | NO |  | Customer
32 | customer_city |  |  | StringType |  |  | NO | false | NO |  | Customer
33 | customer_address |  |  | StringType |  |  | NO | false | NO |  | Customer
34 | customer_postcode |  |  | StringType |  |  | NO | false | NO |  | Customer
35 | customer_income |  |  | DecimalType |  |  | NO | false | NO |  | Customer
36 | customer_expected_amount |  |  | DecimalType |  |  | NO | false | YES |  | Customer
37 | customer_bank_branch_id |  |  | StringType |  |  | NO | false | NO |  | Customer
38 | customer_bank |  |  | StringType |  |  | NO | false | NO |  | Customer
39 | customer_loan_id |  |  | StringType |  |  | NO | false | NO |  | Customer
40 | customer_loan_amount |  |  | DecimalType |  |  | NO | false | NO |  | Customer
41 | customer_loan_base_balance |  |  | DecimalType |  |  | NO | false | NO |  | Customer
42 | customer_credit_limit |  |  | DecimalType |  |  | NO | false | NO |  | Customer
43 | customer_expected_installement_amount |  |  | DecimalType |  |  | NO | false | NO |  | Customer
Counterparty information
44 | counterparty_id |  | Counterparty unique identifier | StringType |  |  | YES | true | NO |  | Counterparty
45 | counterparty_name |  | Counterparty name | StringType |  |  | YES | true | NO |  | Counterparty
46 | counterparty_type |  |  | StringType |  |  | YES | false | NO |  | Counterparty
47 | counterparty_account_number |  |  | StringType |  |  | NO | false | NO |  | Counterparty
48 | counterparty_sort_code |  |  | StringType |  |  | NO | false | NO |  | Counterparty
49 | counterparty_date_of_birth |  |  | DateTimeType | YYYY-MM-DD |  | NO | false | NO |  | Counterparty
50 | counterparty_country |  |  | StringType |  |  | NO | false | YES |  | Counterparty
51 | counterparty_bank_country |  |  | StringType |  |  | NO | false | YES |  | Counterparty
52 | counterparty_state |  |  | StringType |  |  | NO | false | NO |  | Counterparty
53 | counterparty_address |  |  | StringType |  |  | NO | false | NO |  | Counterparty
54 | counterparty_city |  |  | StringType |  |  | NO | false | NO |  | Counterparty
55 | counterparty_postcode |  |  | StringType |  |  | NO | false | NO |  | Counterparty
56 | counterparty_reference |  |  | StringType |  |  | NO | false | NO |  | Counterparty
Counterparty institution
57 | counterparty_institution_id |  |  | StringType |  |  | NO | false | NO |  | Counterparty
58 | counterparty_institution_name |  |  | StringType |  |  | NO | false | NO |  | Counterparty

## Sheet12
tx_id | tx_date_time | tx_direction | tx_type | tx_base_currency | tx_base_amount | tx_currency | tx_amount | tx_reference_text | tx_product | tx_payment_channel | tx_mcc_code | tx_loan_funding_datetime | tx_loan_settlement_datetime | tx_loan_expected_repayment_datetime | tx_loan_monthy_expected_installment_amount | tx_calendar_year | tx_calendar_month | customer_id | customer_name | customer_type | customer_account_balance | customer_account_currency | customer_base_account_balance | customer_account_number | customer_account_type | customer_sort_code | customer_risk_category | customer_date_of_birth | customer_country | customer_state | customer_city | customer_address | customer_postcode | customer_income | customer_expected_amount | customer_bank_branch_id | customer_bank | customer_loan_id | customer_loan_amount | customer_loan_base_balance | customer_credit_limit | customer_expected_installement_amount | counterparty_id | counterparty_name | counterparty_type | counterparty_account_number | counterparty_sort_code | counterparty_date_of_birth | counterparty_country | counterparty_bank_country | counterparty_state | counterparty_address | counterparty_city | counterparty_postcode | counterparty_reference | counterparty_institution_id | counterparty_institution_name

## 3. Rules & Actions
Actions
Priority | Name | Description
10 | Hard Stop | Transaction is flagged for review and blocked from proceeding |  | When requesting new rules, please provide the name and a detailed description. SEs will then scope the rule and complete the rest of the fields,
5 | Soft Stop | Transaction is flagged for reviewed but allowed to proceed
Rules |  | For TM Standard Rules - Please Navigate to tab - 'TM Standard Rules' and tick the checkbox for auto population of the selected rule.
Parameters
# | Short Code | Name | Description | Rule Logic | Rule Logic Explained | Status | Segment(s) | Alert Type | 1 | 2 | 3 | Module | Workflow Enforcement | Comments
1 | P-HVO | [Payments] - High Velocity outbound | Number of outgoing transactions over a short period is greater than limit | tx_direction = Outbound AND count of tx per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Outbound Has the customer had more than a set [Number] of Outbound transactions in the most recent 7 days? | [8 empty] | Third Party Transaction | Help
2 | P-HSUMO | [Payments] - High Cumulative Amount - Outbound | Sum of outgoing transactions over a short period is greater than a limit | tx_direction = Outbound AND sum of tx_base_amount per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Outbound Has the customer's sum of Outbound transactions in the most recent 7 days been greater than a set [Amount]? | [8 empty] | Third Party Transaction - only inbound
3 | P-LVAL | [Payments] - Unexpected Value | Transaction value exceeds customer declared limit | customer_expected_amount [Default:0] ≠ 0 AND tx_base_amount > customer_expected_amount * [Factor] | Was the customer's expected amount provided (in base currency)? Was the transaction more than a set [Factor] times greater than the customer's expected transacion value?
4 | OUT>%IN | Movement of Funds - Outbound (rename rule and clean up the description) | Sum of incoming transactions similar to sum of outgoing transactions Totals of incoming is 100+/-[Y] precentage of outgoing transactions over the last {time period} Rule logic: compare the sum of outgoing and sum of incoming transactions over a set number of days. and if they are about the same - we need to alert. ""About the same"" can be calculated any way we choose. My suggestion would be to use a factor for this calculation. sum of incoming transactions is 100+/-[FACTOR] percentage of sum of outgoing transactions over the last {time period}. Explanation: So that if factor = 20, for example, then we use (100-20)%, and (100+20)% as the limits: 80% * sum of outgoing <sum of incoming <120% sum of outgoing" | sum of tx_base_amount per {customer_id} [Filter: tx_direction = Outbound] in 30 days > [Amount] AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Outbound] in 30 days ≥ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 30 days * ([Percentage_Low]/100) } AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Outbound] in 30 days ≤ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 30 days * ([Percentage_High]/100) } | Has the sum of the cusotmer's Outbound transactions withdrawn over the last 30 days, been greater than a set [Amount]? (A condition that is used to exclude cases when more than a set percentages of the deposited sum has been withdrawn, although the withdrawwn sum was of an irrelevant amount) Has the customer's sum of Outobund transactions within the last 30 days been between the set [Percentage_Low] and [Percentage_High]% of the cusotmer's sum of Inbound transactions that have been deposited within the same 30 days?
5 | STRIN | Structuring - Inbound | Significant number of low value incoming transactions just below a threshold | tx_direction = Inbound AND tx_base_amount ≥ 9950 AND tx_base_amount < 10000 AND count of tx per {customer_id & tx_direction } [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction an Inbound transaction? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the customer had morethan a set [Number] of Inbound transactions within 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)??
6 | STROUT | Structuring - Outbound | Significant number of low value outgoing transactions just below a threshold | tx_direction = Outbound AND tx_base_amount ≥ 9950 AND tx_base_amount < 10000 AND count of tx per {customer_id & tx_direction } [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction an Outbound transaction? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the customer had morethan a set [Number] of Outbound transactions within 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)?? | [10 empty] | For example: to enable a rule comparing the transaction value to the total value of the account, both values will need to be included within the transaction
7 | MCOC_1 | Multiple Customers, One Counterparty (rename these rules) | Transactions to/from multiple customers from/to the same counterparty | unique count of customer_id per {counteprarty_id} in 30 days > [Number] AND count of tx per {customer_id & counteprarty_id} in 30 days = 1 | Has the counterpatry transacted with more than a set [Number] of custoemrs within the last 30 days? Has this been the first transaction between this customer and counteraprty within the last 30 days?
8 | OCMC_1 | Multiple Counterparties, One Customer | Transactions from multiple counterparties to the same customer | unique count of counterparty_id per {customer_id} in 30 days > [Number] AND count of tx per {customer_id & counteprarty_id} in 30 days = 1 | Has the customer transacted with more than a set [Number] of counterparties within the last 30 days? Has this been the first transaction between this customer and counteraprty within the last 30 days?
9 | SUMCCO | High Cumulative Amount - Outbound - Counterparty | Significant number of transactions sent to a Counterparty over a short period | tx_direction = Outbound AND sum of tx_base_amount per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Outbound transaction? Has the sum of Outbound transactions that this customer has sent to a single countearprty within 14 days been greater than a set [Amount]?
10 | NUMCCI | High Velocity - Inbound - Counterparty | High number of transactions received from a Counterparty over a short period | tx_direction = Inbound AND count of tx per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Inbound transaction? Has the number of Inbound transactions that this customer has received from a single countearprty within 14 days been greater than a set [Number]?
11 | NUMCCO | High Velocity - Outbound - Counterparty | High number of transactions sent to a Counterparty over a short period | tx_direction = Outbound AND count of tx per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Outbound transaction? Has the number of Outbound transactions that this customer has sent to a single countearprty within 14 days been greater than a set [Number]?
12
13
14
15

## 4. Segments
Segments
|  |  |  | RULES | [27 empty] | Help
|  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
|  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Name | Description | Priority | Logic | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action | Parameters | Action |  | Breaking down your transactions into segments allows you to apply different rules and/or rule parameters to different sub-sections of your data. For example, if you want to apply different limits (i.e. parameters) to high risk countries or accounts above a certain balance. Setting priority levels for each segment helps to further identify which sections are of highest importance to your Transaction Monitoring process. You can create as many segments as you want as long as no two segments can apply to the same transaction within the same priority level. Once you have created your segmets you can then identify which rules you want to apply within each segment
ALL TRANSACTIONS | Default base segment to identify rules to be run against all transactions. Please do not remove this row though you can change the parameters used in the rules. | N/A | N/A

## 5.1 Workflow for alerts
Workflow States
From |  |  |  |  | To
State Name | Description |  |  |  | In Review | Accepted (end) | Rejected (end) | Escalated
In Review | Initial state used to highlight alert should be reviewed |  |  |  |  | TRUE | TRUE | TRUE | Help
Accepted (end) | State for accepted alerts |  |  |  | FALSE |  | FALSE | FALSE |  | In this section please indicate different review states you wish to have implemented within the platform. You will also need to indicate the permitted state changes you wish to have implemented.
Rejected (end) | State for rejected alerts |  |  |  | FALSE | FALSE |  | FALSE
Escalated | State to highlight alert should be reviewed by a senior compliance officer |  |  |  | FALSE | TRUE | TRUE
For example: an escalated case can only be changed to "accept" or "decline"
Transition | Read Only | Analyst | Manager | Officer | Admin | Diagram of Workflow
In Review -> Accepted | X | ✔ | ✔ | ✔ | ✔
In Review -> Rejected | X | ✔ | ✔ | ✔ | ✔
In Review -> Escalated | X | ✔ | ✔ | ✔ | ✔
Escalated -> Accepted | X | X | ✔ | ✔ | ✔
Escalated -> Rejected | X | X | ✔ | ✔ | ✔
Note: Unhide additional rows if required
Alert Assignment | Read Only | Analyst | Manager | Officer | Admin
State = In Review | X | ✔ | ✔ | ✔ | ✔
State = Accepted | X | X | ✔ | ✔ | ✔
State = Rejected | X | X | ✔ | ✔ | ✔
State = Escalated | X | X | ✔ | ✔ | ✔
Note: Unhide additional rows if required
In Review
Escalated
Accepted
Rejected

## 5.2 Workflow for cases
Workflow Cases
From |  |  |  |  | To
State Name | Description |  |  |  | Created | Investigating | Escalated | Reported | Closed
Created | Initial state for cases |  |  |  | TRUE | TRUE | FALSE | FALSE | FALSE | Help
Investigating | Case is being investigated |  |  |  | FALSE | TRUE | TRUE | FALSE | TRUE |  | In this section please indicate different review states you wish to have implemented within the platform. You will also need to indicate the permitted state changes you wish to have implemented.
Escalated | Case has been escalated |  |  |  | FALSE | FALSE | TRUE | TRUE | TRUE
Reported | Case has been reported |  |  |  | FALSE | FALSE | FALSE | TRUE | FALSE
Closed | Case has been closed as not suspicious |  |  |  | FALSE | FALSE | FALSE | FALSE
For example: an escalated case can only be changed to "accept" or "decline" It is helpful to create a basic workflow diagram stating the relevant states and the actions a user can take from each task. This can then be used to derive this table.
Transition | Read Only | Analyst | Manager | Officer | Admin | Diagram of Workflow
Created -> Investigating | X | X | X | X | ✔
Investigating -> Escalated | X | X | X | X | ✔
Escalated -> Reported | X | X | X | X | ✔
Investigating -> Closed | X | X | X | X | ✔
Escalated -> Closed | X | X | X | X | ✔
Note: Unhide additional rows if required
Case Assignment | Read Only | Analyst | Manager | Officer | Admin
Created | X | X | X | ✔ | ✔
Investigating | X | X | ✔ | ✔ | ✔
Escalated | X | X | ✔ | ✔ | ✔
Reported | X | X | ✔ | ✔ | ✔
Closed | X | X | X | X | X
Note: Unhide additional rows if required
Created
Investigating
Escalated
Reported
Closed

## 6.1 System Config
Security
IP Whitelisting | No
Settings
Name | Value
Mandatory comment on assigning a user (alert)
Mandatory comment on changing state (alert)
Mandatory comment on assigning a user (case)
Mandatory comment on changing state (case)
MFA
MFA Enforce Enrolment
Show age of alert
SAR
Alert Risk Level by Age
Risk | Max Range | Min Range
Low | 24-18h | 6-0h
Medium | 7-6d | 2-1d
Increased | 28-21d | 14-7d
High | 180d+ | 60-28d
Management Information Reports
Report Name | Value
Alerts per rule vs time
Alerts per rule vs end state
Number of true/false positive hits per screening rule
Sending Details | Value
Email(s)
Day of the month
SAR Details
Name | Details
Address
Full Name
Alternate Name
Organisation Classification Type Sub Type
Party Identification
Primary Regulatory Type Code
Preset Comments
Comments

## 6.2 Users
Users
Username | First Name | Last Name | Email | API Token | UAT User | Role
Note: if you are uploading transactions via the API, you will need a user to generate an API token with. This should use a generic email (e.g. ca_token@yourdomain). This is done in your best interest to avoid accidental deletion of Accounts linked to API Tokens should there be any personnel changes.

## 7. Permissions
Permissions
Category | Name | Read-Only | Analyst | Manager | Officer | Admin
Alert | Transitions between States | See 5.1 Workflow for alerts
Alert | Assign Alert to User | See 5.1 Workflow for alerts
Alert | Update Any Alert | 0 | 0 | 0 | 1 | 1
Alert | View, search & filter alert list | 1 | 1 | 1 | 1 | 1
Alert | Update alert | 0 | 1 | 1 | 1 | 1
Alert | View alert details | 1 | 1 | 1 | 1 | 1
Case | Update case | 0 | 0 | 1 | 1 | 1
Case | Update Any Case | 0 | 0 | 0 | 0 | 1
Case | Create case | 0 | 0 | 1 | 1 | 1
Case | Delete case | 0 | 0 | 0 | 1 | 1
Case | View case details | 1 | 1 | 1 | 1 | 1
Case | View, search & filter cases list | 1 | 1 | 1 | 1 | 1
Case | Assign Case to User | See 5.2 Workflow for cases
Case | Transitions between Cases | See 5.2 Workflow for cases
Data Source | Upload spreadsheet | 1 | 1 | 1 | 1 | 1
Data Source | Delete spreadsheet | 0 | 1 | 1 | 1 | 1
Entity | View Entity list | 1 | 1 | 1 | 1 | 1
Entity | View Entity detail | 1 | 1 | 1 | 1 | 1
Exported Content | View, search & filter Exported Content list | 1 | 1 | 1 | 1 | 1
Exported Content | Add Exported Content | 0 | 1 | 1 | 1 | 1
Exported Content | View Exported Content details | 1 | 1 | 1 | 1 | 1
Log | View log list | 1 | 1 | 1 | 1 | 1
Log | View comment list | 1 | 1 | 1 | 1 | 1
Log | Create comment | 0 | 1 | 1 | 1 | 1
Log | Delete own comment | 0 | 1 | 1 | 1 | 1
Log | Delete any comment | 0 | 0 | 0 | 0 | 1
Log | View log detail | 1 | 1 | 1 | 1 | 1
Log | View attachment list | 1 | 1 | 1 | 1 | 1
Log | Upload attachment | 0 | 1 | 1 | 1 | 1
Log | View attachment detail | 1 | 1 | 1 | 1 | 1
Log | Delete own attachment | 0 | 1 | 1 | 1 | 1
Log | Delete any attachment | 0 | 0 | 0 | 0 | 1
Log | View comment detail | 1 | 1 | 1 | 1 | 1
Lookup List Enricher | View, search & filter Lookup List Enricher list | 1 | 1 | 1 | 1 | 1
Lookup List Enricher | View Lookup List Enricher details | 1 | 1 | 1 | 1 | 1
Lookup List Enricher | Add Lookup List Enricher | 0 | 0 | 0 | 0 | 1
Lookup List Enricher | Delete Lookup List Enricher | 0 | 0 | 0 | 0 | 1
Lookup List Enricher | Change Lookup List Enricher | 0 | 0 | 0 | 0 | 1
Lookup List Item | View, search & filter Lookup List Item list | 0 | 0 | 0 | 0 | 1
Risk Word List | View Risk Word List details (Screening) | 0 | 0 | 0 | 0 | 1
Risk Word List | Add Risk Word List (Screening) | 0 | 0 | 0 | 0 | 1
Risk Word List | Change Risk Word List (Screening) | 0 | 0 | 0 | 0 | 1
Risk Word List | View, search & filter Risk Word List list (Screening) | 0 | 0 | 0 | 0 | 1
Rule | View rule details | 0 | 0 | 1 | 1 | 1
Rule | View, search & filter rule list | 1 | 0 | 1 | 1 | 1
Rule | Create rule config | 0 | 0 | 0 | 0 | 1
Rule | Change rule config | 0 | 0 | 0 | 0 | 1
Rule | View rule config details | 0 | 0 | 1 | 1 | 1
Rule | View, search & filter rule config list | 0 | 0 | 1 | 1 | 1
SAR | Can View/Submit/Modify SARs | 0 | 0 | 1 | 1 | 1
Segment | View segment details | 0 | 0 | 0 | 0 | 1
Segment | View, search & filter segment list | 0 | 0 | 0 | 0 | 1
Transaction | View, search & filter Transaction list | 1 | 1 | 1 | 1 | 1
Transaction | View Transaction details | 1 | 1 | 1 | 1 | 1
User | View, search & filter user list | 1 | 1 | 1 | 1 | 1
User | View user details | 0 | 0 | 0 | 0 | 1
User | Add user | 0 | 0 | 0 | 0 | 1
User | Change user | 0 | 0 | 0 | 0 | 1
User | Reset user password | 0 | 0 | 0 | 0 | 1
User | Activate / Deactivate user | 0 | 0 | 0 | 0 | 1

## 8. Lookup Lists Summary
Lookup Lists Summary
Lookup List Name
Used in Rule Codes
Input field
Output field
Lookup List Name
Used in Rule Codes
Input field
Output field
Lookup List Name
Used in Rule Codes
Input field
Output field
Lookup List Name
Used in Rule Codes
Input field
Output field
Lookup List Name
Used in Rule Codes
Input field
Output field
Lookup List Name
Used in Rule Codes
Input field
Output field

## 9. APIUpload Information
Upload Details
Source Format
Upload Method
Example Upload
API Token Details | Note: if you are uploading transactions via the API, you will need a user to generate an API token with. This should use a generic email (e.g. ca_token@yourdomain). This is done in your best interest to avoid accidental deletion of Accounts linked to API Tokens should there be any personnel changes.
Token User Email
Token Username
API Endpoints
QA
Endpoint Secure Zone Owner
Endpoint Secure Zone Link
Prod
Endpoint Secure Zone Owner
Endpoint Secure Zone Link
Webhooks
QA
Webhooks Secure Zone Owner
Webhooks Secure Zone Link
Prod
Webhooks Secure Zone Owner
Webhooks Secure Zone Link

## 9. Build Questions (hidden)
Build Questions
# | Date Raised | Raised By | Status | Context | Query | Answer | Changes Implemented
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## 10. Post Go-Live Changes (hidden)
Post Go-Live Changes
# | Date Raised | JIRA Ticket | Context | Request | Comments | Changes Implemented | Downtime Required | Signed off Date | Go-live Date | CA Migration Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Config
Configurations - USED BY CA
Data Types | UI Visibility | Upload Models | Roles | Operator | Status | Statuses |  | UK bank holidays
StringType | Detail | Manual Batch | Read-Only | equals | Open | Not Started | Transaction | 2020-04-10 | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DateTimeType | Summary | API - Batch | Analyst | greater than | Response | In Progress | Grouped: Customer | 2020-04-13 | Customer | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DecimalType | Detail & Summary | API-Single Transaction | Manager | less than | Further Query | On Hold | Grouped: Counterparty | 2020-05-08 | Counterparty | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IntegerType | None |  | Officer | greater or equal to | Resolved | Completed |  | 2020-05-25 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DateType |  |  | Admin | less than or equal to |  |  |  | 2020-08-31 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | not equals |  |  |  | 2020-12-25 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | 2020-12-28 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | 2021-01-01 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2021-04-02
2021-04-05
|  | API - Batch | [5 empty] | 2021-05-03 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | API - Single Transaction | [5 empty] | 2021-05-31
|  | Platform - Manual Batch | [5 empty] | 2021-08-30
2021-12-27
2021-12-28

## TM Standard Rules
TM Standard Rules Library
# | Short Code | Rule name | Description | Rule Logic | Rule Logic Explained | Selection
1 | CPO | Cash Payments Only | Client only transacts in cash over a set period Number of cash transactions is greater than the limit over a period of time during which no other transaction types have occurred | tx_type = cash AND count of tx {customer_id & tx_type} in 30 days > [Number] AND count of tx per {customer_id} [Filter tx_type ≠ cash] in 30 days = 0 | Was the transaction a cash transaction? Has the customer had more than a set [Number] of cash transactions over tha last 30 days? Has the customer had 0 transactions in the last 30 days that have not been cash transactions? | FALSE
2 | HVCD->CW | High Value Cummulated Sum of Cash Deposits Followed By Cash Withdrawal | High cumulative value of cash deposits followed by a high value cash withdrawal Cash withdrawal of X is greater than limit of limit Y and is made within [time period] of a high value cash deposit of Z | tx_type = cash AND tx_direction = Outbound AND tx_base_amount > [Amount_Outbound] AND sum of tx_base_amount {per customer_id & tx_type} [Filter: tx_direction = Inbound] in 1d > [Amount_Inbound] | Was the evaluated transaciton an cash transaction? Was the cash transaction an Outbound transction? Was the Outbound cash transactions greater than a set [Amount_Outbound]? Has the sum of the customer's Inbound cash transactions in the last 1 day been greater than a set [Amount_Inbound]? | FALSE
3 | OP->3PCD | Outgoing Payment Followed By 3rd Party Deposit | Outgoing payment followed by a deposit made by a 3rd party check Outgoing payment of X followed a 3rd party check deposit within [time period] | tx_type = [Type] AND tx_direction = Inbound AND tx_base_amount > [Amount} AND count of tx per {customer_id} [Filter: tx_direction Outbound] in 1d ≥ [Number] | Was the evaluated transaction a 3rd party check transaction? Was the 3rd party check an Inbound transaction (deposit)? Was the Inbound 3rd party check greater than a set [Amount]? Did the customer have at least a set [Number] of Inbound transactions within the evaluated day? | FALSE
4 | HVC-I | High Velocity Cash Deposit | Number of cash deposits over a short period is greater than limit Number of cash deposits is greater than limit of X over [time period] | tx_type = [Type] AND tx_direction = [Direction] AND count of tx per {customer_id, tx_direction & tx_type} in 7d > [Number] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Inbound transaction? Has the customer had more than a set [Number] of Inbound cash transactions in the last 7 days? | FALSE
5 | HVC-O | High Velocity Cash Withdrawal | Number of cash withdrawals over a short period is greater than limit Number of cash withdrawals is greater than limit of X over [time period] | tx_type = [Type] AND tx_direction = [Direction] AND count of tx per {customer_id, tx_direction & tx_type} in 7d > [Number] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Outbound transaction? Has the customer had more than a set [Number] of Outbound cash transactions in the last 7 days? | FALSE
6 | HSUMC-I | High Cumulative value of Cash Deposit | Sum of cash deposits over a set period is greater than limit Total sum X of cash deposits over [time period] is greater than limit of Y | tx_type = [Type] AND tx_direction = [Direction] AND sum of tx_base_amount {per customer_id, tx_direction & tx_type} in 7d > [Amount] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Outbound transaction? Has the customer's sum of Outbound cash transactions over the most recent 7 days been greater than a set [Amount]? | FALSE
7 | HSUMC-O | High Cumulative value of Cash Withdrawals | Sum of cash withdrawals over a set period is greater than limit Total sum X of cash withdrawals over [time period] is greater than limit of Y | tx_type = [Type] AND tx_direction = [Direction] AND sum of tx_base_amount {per customer_id, tx_direction & tx_type} in 7d > [Amount] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Inbound transaction? Has the customer's sum of Inbound cash transactions over the most recent 7 days been greater than a set [Amount]? | FALSE
8 | HVALC-O | High Value Cash Withdrawal | A single cash withdrawal is greater than limit | tx_type = [Type] AND tx_direction = [Direction] AND tx_Base_amount > [Amount] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Outbound transaction? Was the Outbound cash transaction greater than a set [Amount]? | FALSE
9 | HVALC-I | High Value Cash Deposit | A single cash deposit is greater than limit | tx_type = cash AND tx_direction = Inbound AND tx_Base_amount > [Amount] | Was the evaluated transaction a cash trnasaction? Was the cash transaction an Inbound transaction? Was the Inbound cash transaction greater than a set [Amount]? | FALSE
10 | HV3PC-I | High Velocity Incoming 3rd party Checks | Number of incoming checks from a third party is greater than limit Number of 3rd party check deposits over [time period] is greater than limit of X | tx_type = [Type] AND tx_direction = [Direction] AND count of tx per {customer_id, tx_direction & tx_type} in 7d > [Number] | Was the transaction a 3rd party check transaction? Was the 3rd party check transaction an Inbound transaction? Has the customer received more than a set [Number] of Inbound 3rd party check transations in the most recent 7 days? | FALSE
11 | P-%BAL | [Payments] - Percentage of Balance | Outgoing transaction value is almost reaching account balance Note: The rule assumes a balance is received before the transaction, and it then calculates what was the balance after the transaction. | tx_direction = Outbound AND customer_base_account_balance [Default: -10000000000000000] ≥ [Balance] AND customer_base_account_balance [Default: -10000000000000000] - tx_base_amount ≤ 0 OR customer_base_account_balance [Default: -10000000000000000] - tx_base_amount > 0 AND tx_base_amount > customer_base_account_balance [Default: -10000000000000000] * [Percentage]/100 | Was the transaction Outbound Was the account base balance at least of the set [Balance] (where account base balance is understood to be received as it was prior to the transaction)? (Excludes cases where a high % of balance was withdrawn, but the balance was low) Was the full balance withdrawn or the account overdrawn (inferred from the account base balance being 0 or less prior to the transaction following which this utbound transaction happens)? OR Was the Outbound transaction greater than a set [Percentage] of the account balance (prior to the transaction)? | FALSE
12 | P-TLO | [Payments] - Payment Limit - Outbound | Outgoing transaction value is greater than limit | tx_direction = Outbound AND tx_base_amount > [Amount] | Was the transaction Outbound Was the transaction greater than a set [Amount]? | FALSE
13 | P-TLI | [Payments] - Payment Limit - Inbound | Incoming transaction value is greater than limit | tx_direction = Inbound AND tx_base_amount > [Amount] | Was the transaction Inbound Was the transaction greater than a set [Amount]? | FALSE
14 | P-HVI | [Payments] - High Velocity Inbound | Number of incoming transactions over a short period is greater than limit | tx_direction = Inbound AND count of tx per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Inbound Has the customer had more than a set [Number] of Inbound transactions in the most recent 7 days? | FALSE
15 | P-HVO | [Payments] - High Velocity outbound | Number of outgoing transactions over a short period is greater than limit | tx_direction = Outbound AND count of tx per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Outbound Has the customer had more than a set [Number] of Outbound transactions in the most recent 7 days? | TRUE
16 | P-HSUMI | [Payments] - High Cumulative Amount - Inbound | Sum of incoming transactions over a short period is greater than a limit | tx_direction = Inbound AND sum of tx_base_amount per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Inbound Has the customer's sum of Inbound transactions in the most recent 7 days been greater than a set [Amount]? | FALSE
17 | P-HSUMO | [Payments] - High Cumulative Amount - Outbound | Sum of outgoing transactions over a short period is greater than a limit | tx_direction = Outbound AND sum of tx_base_amount per {customer_id & tx_direction} in 7d > [Number] | Was the transaction Outbound Has the customer's sum of Outbound transactions in the most recent 7 days been greater than a set [Amount]? | TRUE
18 | P-LBAL | [Payments] - High Account Balance | Account balance at the end of a transaction is greater than a limit Note: This rule will work for any balance, either before or after the transaction | tx_direction = Outbound AND sum of tx_base_amount per {customer_id & tx_direction} in 7d > [Number] | Was the customer's account balance provided (in base currency)? Was the account balance (in base currency) greater than a set [Balance]? | FALSE
19 | P-LVAL | [Payments] - Unexpected Value | Transaction value exceeds customer declared limit | customer_expected_amount [Default:0] ≠ 0 AND tx_base_amount > customer_expected_amount * [Factor] | Was the customer's expected amount provided (in base currency)? Was the transaction more than a set [Factor] times greater than the customer's expected transacion value? | TRUE
20 | P-1st | [Payments] - First Transaction | First payment of a Customer | count of transactions per {per customer_id} = 1 | Has this been the first tranaction for this customer? | FALSE
21 | P-2nd | [Payments] - Second transaction | Second payment of a Customer | count of transactions per {per customer_id} = 2 | Has this been the second tranaction for this customer? | FALSE
22 | P-SUMCI3 | [Payments] - High Cumulative Amount - Inbound - Counterparty | High cumulative amount of transactions received from a Counterparty in 3d | tx_direction = Inbound AND sum of tx_base_amount per {customer_id, counterparty_id & tx_direction} in 3d > [Amount] | Was the transaction Inbound? Has the sum of Inbound transactions a customer recieved from a single counteparty over 3 days been greater than a set [Amount]? | FALSE
23 | P-SUMCO3 | [Payments] - High Cumulative Amount - Outbound - Counterparty | High cumulative amount of transactions sent to a Counterparty in 3d | tx_direction = Outbound AND sum of tx_base_amount per {customer_id, counterparty_id & tx_direction} in 3d > [Amount] | Was the transaction Outbound? Has the sum of Outbound transactions a customer sent to a single counteparty over 3 days been greater than a set [Amount]? | FALSE
Similar amounts of withdrawal and deposit
24 | OUT>%IN | Movement of Funds - Outbound (rename rule and clean up the description) | Sum of incoming transactions similar to sum of outgoing transactions Totals of incoming is 100+/-[Y] precentage of outgoing transactions over the last {time period} Rule logic: compare the sum of outgoing and sum of incoming transactions over a set number of days. and if they are about the same - we need to alert. ""About the same"" can be calculated any way we choose. My suggestion would be to use a factor for this calculation. sum of incoming transactions is 100+/-[FACTOR] percentage of sum of outgoing transactions over the last {time period}. Explanation: So that if factor = 20, for example, then we use (100-20)%, and (100+20)% as the limits: 80% * sum of outgoing <sum of incoming <120% sum of outgoing" | sum of tx_base_amount per {customer_id} [Filter: tx_direction = Outbound] in 30 days > [Amount] AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Outbound] in 30 days ≥ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 30 days * ([Percentage_Low]/100) } AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Outbound] in 30 days ≤ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 30 days * ([Percentage_High]/100) } | Has the sum of the cusotmer's Outbound transactions withdrawn over the last 30 days, been greater than a set [Amount]? (A condition that is used to exclude cases when more than a set percentages of the deposited sum has been withdrawn, although the withdrawwn sum was of an irrelevant amount) Has the customer's sum of Outobund transactions within the last 30 days been between the set [Percentage_Low] and [Percentage_High]% of the cusotmer's sum of Inbound transactions that have been deposited within the same 30 days? | TRUE
25 | IN>%OUT | Movement of Funds - Inbound |  | sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 30 days > [Amount] AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Inbound] in 30 days ≥ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Outbound] in 30 days * ([Percentage_Low]/100) } AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: tx_direction = Inbound] in 30 days ≤ { sum of tx_base_amount per {customer_id} [Filter: tx_direction = Outbound] in 30 days * ([Percentage_High]/100) } | Has the sum of the cusotmer's Inbound transactions deposited over the last 30 days, been greater than a set [Amount]? (A condition that is used to exclude cases when more than a set percentages of the withdrawn sum has been deposited, although the deposited sum was of an irrelevant amount) Has the customer's sum of Inobund transactions within the last 30 days been between the set [Percentage_Low] and [Percentage_High]% of the cusotmer's sum of Outbound transactions that have been withdrawn within the same 30 days? | FALSE
26 | IN-OUT-1 | High Value Outgoing Transaction, High Number of Inbound Deposits | Significant number of incoming transactions followed by a large outgoing transaction direction = outgoing AND amount > [value] AND number of incoming trx below a limit [number] over last {time period} | tx_direction = Outbound AND tx_base_amount > [Amount] AND count of tx per {customer_id} [Filter: tx_direction = Inbound] in 14 days > [Number] AND tx_base_amount ≥ { [Percentage]/100 * sum of tx_base_amount per {customer_id} [Filter: tx_direction = Inbound] in 14 days } | Was the transaction that trigger this rule an Outbound tx? Was the Outbound transaction greater than a set [Limit]? Has the cusotmer had more than a set Number of Inbound transactions within the last 14 days? Was the evaluated Outbound transaction at least as large as a set [Percentage] of the customer's sum of Inbound transations received within the last 14 days? | FALSE
27 | IN-OUT-2 | High Value Outgoing Transaction, High Number of Inbound deposits Rename rule (dupliucation with the above) | trx direction = outgoing AND trx amount > [value] AND number of incoming trx < [number] over last {time period} AND each incoming trx is below < value (value can be hard coded) | tx_direction = Outbound AND tx_base_amount > [Amount] AND count of tx per {customer_id} [Filter: tx_direction = Inbound AND tx_base_amount > 0] in 14 days ≥ [Number] | Was the transaction that trigger this rule an Outbound tx? Was the Outbound transaction greater than a set [Limit]? Has the cusotmer had at least a set Number of Inbound transactions, each with values greater than 0. within the last 14 days? | FALSE
Structuring
28 | STRIN | Structuring - Inbound | Significant number of low value incoming transactions just below a threshold | tx_direction = Inbound AND tx_base_amount ≥ 9950 AND tx_base_amount < 10000 AND count of tx per {customer_id & tx_direction } [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction an Inbound transaction? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the customer had morethan a set [Number] of Inbound transactions within 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)?? | TRUE
29 | STROUT | Structuring - Outbound | Significant number of low value outgoing transactions just below a threshold | tx_direction = Outbound AND tx_base_amount ≥ 9950 AND tx_base_amount < 10000 AND count of tx per {customer_id & tx_direction } [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction an Outbound transaction? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the customer had morethan a set [Number] of Outbound transactions within 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)?? | TRUE
30 | STRCASH | Multiple Low Value transactions (Cash Deposits) | Significant number of low value cash deposits just below a threshold | tx_direction = Inbound AND tx_type = [Type] AND tx_base_amount ≥ 9950 AND base_amount < 10000 AND count of tx per {customer_id,tx_type & tx_direction} [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction an Inbound transaction? Was the Inbound transactoin a cash tx? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the customer had morethan a set [Number] of Inbound cash transactions within 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)?? | FALSE
31 | STRBANK | Multiple Low Value transactions (Locations) | Multiple low value deposits performed by the customer from different branches of the bank | tx_direction = Inbound AND tx_base_amount ≥ 9950 AND tx_base_amount < 10000 AND unique count of customer_bank_branch_id per {customer_id, tx_direction & customer_bank} [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > [Number] AND count of tx per {customer_id, tx_direction & customer_bank} [filter: tx_base_amount ≥ 9950 AND tx_base_amount < 10000] in 7 days > 1 | Was the transaction an Inbound transaction? Was the transaction at least of 9,950 (in base currency)? Was the transaction less than 10,000 (in base currency)? Has the cusomer had Inbound transactions at more than 1a set [Number] of different branch IDs of the same bank within the last 7 days, that have each been at least 9,950 but less than 10,000 (in base currency)? Has the customer had more than 1 transactions within the last 7 days with the same bank that have each been at least 9,950 but less than 10,000 (in base currency)? (This condition is purely featured so we can reference the aggregator's output in the message template, thus being able to tell the analyst in the alert context message how many such transactions has the customer had. ) | FALSE
High Risk Products
32 | HRP | High Risk Product | Significant number of high risk product purchases (e.g. prepaid cards, cashier’s checks, money orders, traveler’s checks) Rule name: High Risk Products Rule Logic: trx value > [amount] AND trx_product is on a high_risk_product lookup list | tx_base_amount > [Amount] AND ll_tx_product = [Risk] | Was the transaction greater than a set [Amount]? Was the product designated as a high-risk product (based on a lookup list)? | FALSE
Age Group Risk
33 | VC | Vulnerable Customer | Customer age < 18 or client age >65 | customer_date_of_birth (Default: 1900-01-01T00:00:00+00:00) ≠ 1900-01-01T00:00:00+00:00 AND {tx_date_time - customer_date_of_birth (Default: 1900-01-01T00:00:00+00:00)}/365.25 > [Age_High] OR {tx_date_time - customer_date_of_birth (Default: 1900-01-01T00:00:00+00:00)}/365.25 < [Age_Low] | Was the customer's date of birth provided? Is the customer older than 65? Is the customer younger than 18? | FALSE
Round Amounts
34 | RVT-IN | Round Value Transactions - Inbound | Significant number of incoming transactions involving round amounts | tx_direction = Inbound AND mod of (tx_amount [default: 0.0001], 1000) = 0 AND count of tx per {customer_id & tx_direction] [Filter: mod of (tx_amount [default: 0.0001], 1000) = 0] in 30 days > [Number] AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: mod of (tx_amount [default: 0.0001], 1000) = 0] in 30 days > [Amount] | Was the transaction Inbound? Was the transaction dividable by 1000 without a remainder (in its original currency, not in base currency)? Has the customer had more than a set [Number] of Inbound transactions that have each been dividable by 1000 without a remainder in (their original currencies, not in their values in base currency) within the last 30 days? Has the cusotmer's sum of base currency value of Inbound transactions that have been each dividable by 1000 without a remainder (in their original currencies, not in their values in base currency) been greater than a set [Amount] within the last 30 days? | FALSE
35 | RVT-OUT | Round Value Transactions - Outbound | Significant number of outgoing transactions involving round amounts | tx_direction = Outbound AND mod of (tx_amount [default: 0.0001], 1000) = 0 AND count of tx per {customer_id & tx_direction] [Filter: mod of (tx_amount [default: 0.0001], 1000) = 0] in 30 days > [Number] AND sum of tx_base_amount per {customer_id & tx_direction} [Filter: mod of (tx_amount [default: 0.0001], 1000) = 0] in 30 days > [Amount] | Was the transaction Outbound? Was the transaction dividable by 1000 without a remainder (in its original currency, not in base currency)? Has the customer had more than a set [Number] of Outbound transactions that have each been dividable by 1000 without a remainder in (their original currencies, not in their values in base currency) within the last 30 days? Has the cusotmer's sum of base currency value of Outbound transactions that have been each dividable by 1000 without a remainder (in their original currencies, not in their values in base currency) been greater than a set [Amount] within the last 30 days? | FALSE
36 | HNR-IN | High Number of High Value Round Transactions - Inbound | Significant number of incoming transactions involving round amounts | tx_direction = Inbound AND tx_base_amount > 1000 AND mod of (tx_amount [default: 0.0001], 1000) = 0 AND count of tx per {customer_id & tx_direction] [Filter: mod of (tx_amount [default: 0.0001], 1000 AND tx_base_amount > 1000) = 0] in 30 days > [Number] | Was the transaction an Inbound transaction? Was the value of the tarnsaction (in base currency) greter than a set [Amount]? Was the transaction (in its original currency) of a "round amount"? (defined as dividable by 1000 without a remainder) Has the customer had more than a set [Number] of "round" Inbound transactions (dividable by 1000 without a remainder) with values greater than 1000 (in base currency) within 30 days? | FALSE
37 | HNR-OUT | High Number of High Value Round Transactions - Outbound | Significant number of outgoing transactions involving round amounts | tx_direction = Outbound AND tx_base_amount > 1000 AND mod of (tx_amount, 1000) = 0 AND count of tx per {customer_id & tx_direction] [Filter: mod of (tx_amount, 1000 AND tx_base_amount > 1000) = 0] in 30 days > [Number] | Was the transaction an Outbound transaction? Was the value of the tarnsaction (in base currency) greter than a set [Amount]? Was the transaction (in its original currency) of a "round amount"? (defined as dividable by 1000 without a remainder) Has the customer had more than a set [Number] of "round" Outbound transactions (dividable by 1000 without a remainder) with values greater than 1000 (in base currency) within 30 days? | FALSE
Locations/Currencies
38 | HRCOU | High Risk Country | Transaction to or from a country that is designated as high risk | ll_counterparty_country = [Risk] OR ll_counterparty_bank_country = [Risk] AND tx_base_amount > [Amount] | Was the counterparty country classified as [Risk] (based on a lookup list)? Was the coutneraprty bank country classified as a [Risk} risk country (based on a lookup list)? Was the transaction greater than a set [Amount]? | FALSE
39 | NCOU | New Counterparty Country | Transaction to or from a country that has not been used before by this customer | count of tx per {customer_id} over all-time > 1 AND counterparty_country ≠ "" AND count of tx per {customer_id & counterparty_country} [Filter: counterparty_country ≠ ""] over all-time = 1 | Was this not the customer's first-ever transaction? Was the counteprarty country filed populated (since it is a non-required field)? Was this the customer's first transaction with a new counterparty country (when the counterparty country was not empty)? | FALSE
40 | NBCOU | New Counterparty Bank Country (need to update the description as it's a copy of NCOU) | Transaction to or from a bank country that has not been used before by this customer | count of tx per {customer_id} over all-time > 1 AND counterparty_bank_country ≠ "" AND count of tx per {customer_id & counterparty_bank_country} [Filter: counterparty_bank_country ≠ ""] over all-time = 1 | Was this not the customer's first-ever transaction? Was the counteprarty bank country filed populated (since it is a non-required field)? Was this the customer's first transaction with a new counterparty bank country (when the counterparty bank country was not empty)? | FALSE
41 | HRCU | High Risk Currency | Transaction in a currency that is designated as high risk | ll_tx_currency = [Risk] | Was the transaction currency classified as [Risk] (based on a lookup list)? | FALSE
42 | NCU | New Currency | Transaction to or from a currency that has not been used before by this customer | tx_currency (Default: "") ≠ "" AND count of tx per {customer_id} [Filter: tx_currency (Default: "") ≠ ""] over all-time > 1 AND count of tx per {customer_id & tx_currency} [Filter: tx_currency (Default: "") ≠ ""] = 1 | Was the transaction's otriginal currency value provided? Was this not the customer's first-ever transaction? Was this the customer's first transaction with a new currency? | FALSE
ATM Activity
43 | SUMATM | High Value ATM Activity (update rule description as it looks at sum of trx rather than single value) | High value of ATM activity over a short period High value single ATM transaction | tx_type = [Type] AND sum of tx_base_amount per {customer_id & tx_type} in 7 days > [Amount] | Was this transaction of type ATM? Has the sum of a customer's all ATM transactions (deposits as well as withdrawals) been greater than as et [Amount] within 7 days? | FALSE
44 | NUMATM | High Velocity ATM Activity | Significant number of ATM transactions over a short period of time | tx_type= [Type] AND count of tx per {customer_id, tx_type} in 7 days > [Number] | Was this transaction of type ATM? Has the customer had more than a set [Number] of ATM transactions (deposits & withdrawals counted together) in 7 days? | FALSE
45 | STRATM-I | Structuring - ATM - Inbound | Significant number of low value ATM deposits just below a threshold | tx_type = [Type] AND tx_direction = Inbound AND tx_base_amount ≥ 9000 AND tx_base_amount < 10000 AND count of tx per {customer_id, tx_type & tx_direction} [Filter: tx_base_amount ≥ 9000 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction type ATM? Was the transaction direction Inbound? Was the transaction at least of 9,000 value (in base currency)? Was the transaction less than 10,000 value (in base currency) Has the customer had more than a set [Number] of Inbound ATM (ATM deposits) transactions within 7 days, that have each been between at least of 9,000 but less than 10,000 (in base currency) value? | FALSE
46 | STRATM-O | Structuring - ATM - Outbound | Significant number of low value ATM deposits just below a threshold | tx_type = [Type] AND tx_direction = Outbound AND tx_base_amount ≥ 9000 AND tx_base_amount < 10000 AND count of tx per {customer_id, tx_type & tx_direction} [Filter: tx_base_amount ≥ 9000 AND tx_base_amount < 10000] in 7 days > [Number] | Was the transaction type ATM? Was the transaction direction Outbound? Was the transaction at least of 9,000 value (in base currency)? Was the transaction less than 10,000 value (in base currency) Has the customer had more than a set [Number] of Outbound ATM (ATM withdrawals) transactions within 7 days, that have each been between at least of 9,000 but less than 10,000 (in base currency) value? | FALSE
Securities Accounts With Banking Activity
47 | SEC | Securities Account, Little Securities Activity | A securities account with little securities related transactions A securities account is mainly used for payments with little securities related activities | customer_account_type = securities AND sum of tx_base_amount per {customer_id, customer_account_type & customer_account_number} [Filter: tx_type = securities] over 30 days ≤ [Amount] AND sum of sum of tx_base_amount per {customer_id, customer_account_type & customer_account_number} [Filter: tx_type ≠ securities] over 30 days > [Limit] | Was the customer account a securities account? Has the sum of this cusotmer's securities transaction on their securities account been less than or equal to a set [Amount] over 30 days? Has the customer's sum of transaction on accounts other than securities accounts in transactions other than securities transactions been greater than a set [Limit] within the 30 days? | FALSE
Entities
48 | MCOC_1 | Multiple Customers, One Counterparty (rename these rules) | Transactions to/from multiple customers from/to the same counterparty | unique count of customer_id per {counteprarty_id} in 30 days > [Number] AND count of tx per {customer_id & counteprarty_id} in 30 days = 1 | Has the counterpatry transacted with more than a set [Number] of custoemrs within the last 30 days? Has this been the first transaction between this customer and counteraprty within the last 30 days? | TRUE
49 | MCOC_2 | Multiple Customers, One Counterparty | A counterparty that has receive transactions from multiple customers Change description | unique count of customer_id per {counteprarty_id} in 30 days > [Number] | Has the counterpatry transacted with more than a set [Number] of custoemrs within the last 30 days? | FALSE
50 | OCMC_1 | Multiple Counterparties, One Customer | Transactions from multiple counterparties to the same customer | unique count of counterparty_id per {customer_id} in 30 days > [Number] AND count of tx per {customer_id & counteprarty_id} in 30 days = 1 | Has the customer transacted with more than a set [Number] of counterparties within the last 30 days? Has this been the first transaction between this customer and counteraprty within the last 30 days? | TRUE
51 | OCMC_2 | Multiple Counterparties, One Customer | Transactions from multiple counterparties to the same customer | unique count of counterparty_id per {customer_id} in 30 days > [Number] | Has the customer transacted with more than a set [Number] of counterparties within the last 30 days? | FALSE
52 | MCOCI_1 | Multiple Customers, One Counterparty - Inbound (description suould be rephrased - (receieved by the same counterparty, and not related to accounts but customers) | Influx of incoming payments received from the same counterparty to different accounts | tx_direction = Inbound AND unique count of customer_id per {counterparty_id & tx_direction} in 30 days > [Number] AND count of tx per {customer_id, counteprarty_id & tx_direction} in 30 days = 1 | Was the transaciton an Inbound transaction? Has the counterparty sent Inbound transactions to more than a set [Number] of customers within the last 30 days? Has this been the forst Inbound transaction that the counterparty sent to this customer within the last 30 days? | FALSE
53 | MCOCI_2 | Multiple Customers, One Counterparty - Inbound | Influx of incoming payments received from the same counterparty to different accounts | tx_direction = Inbound AND unique count of customer_id per {counterparty_id & tx_direction} in 30 days > [Number] | Was the transaciton an Inbound transaction? Has the counterparty sent Inbound transactions to more than a set [Number] of customers within the last 30 days? | FALSE
54 | OCMCI_1 | Multiple Counterparties, One Customer - Inbound | Influx of incoming payments received from different counterparties to the same account | tx_direction = Inbound AND unique count of counteprarty_id per {customer_id & tx_direction} in 30 days > [Number] AND count of tx per {customer_id, counteprarty_id & tx_direction} in 30 days = 1 | Was the transaciton an Inbound transaction? Has the customer received Inbound transactions from more than a set [Number] of counterparties within the last 30 days? Has this been the first Inbound transaction between this customer and counteraprty within the last 30 days? | FALSE
55 | OCMCI_2 | Multiple Counterparties, One Customer - Inbound | Influx of incoming payments received from different counterparties to the same account | tx_direction = Inbound AND unique count of counteprarty_id per {customer_id & tx_direction} in 30 days > [Number] | Was the transaciton an Inbound transaction? Has the customer received Inbound transactions from more than a set [Number] of counterparties within the last 30 days? | FALSE
56 | MCOCO_1 | Multiple Customers, One Counterparty - Outbound | Outflux of outoing payments received from the same counterparty to different accounts | tx_direction = Outbound AND unique count of customer_id per {counterparty_id & tx_direction} in 30 days > [Number] AND count of tx per {customer_id, counteprarty_id & tx_direction} in 30 days = 1 | Was the transaciton an Outbound transaction? Has the counterparty received Outbound transactions from more than a set [Number] of customers within the last 30 days? Has this been the first Outbound transaction between this customer and counteraprty within the last 30 days? | FALSE
57 | MCOCO_2 | Multiple Customers, One Counterparty - Outbound | Outflux of outoing payments received from the same counterparty to different accounts | tx_direction = Outbound AND unique count of customer_id per {counterparty_id & tx_direction} in 30 days > [Number] | Was the transaciton an Outbound transaction? Has the counterparty received Outbound transactions from more than a set [Number] of customers within the last 30 days? Has this been the first Outbound transaction between this customer and counteraprty within the last 30 days? | FALSE
58 | OCMCO_1 | Multiple Counterparties, One Customer - Outbound | Outflux of outgoing payments received from different counterparties to the same account | tx_direction = Outbound AND unique count of counteprarty_id per {customer_id & tx_direction} in 30 days > [Number] AND count of tx per {customer_id, counteprarty_id & tx_direction} in 30 days = 1 | Was the transaciton an Outbound transaction? Has the customer sent Outbound transactions to more than a set [Number] of counterparties within the last 30 days? Has this been the first Outbound transaction between this customer and counteraprty within the last 30 days? | FALSE
59 | OCMCO_2 | Multiple Counterparties, One Customer - Outbound | Outflux of outgoing payments received from different counterparties to the same account | tx_direction = Outbound AND unique count of counteprarty_id per {customer_id & tx_direction} in 30 days > [Number] | Was the transaciton an Outbound transaction? Has the customer sent Outbound transactions to more than a set [Number] of counterparties within the last 30 days? Has this been the first Outbound transaction between this customer and counteraprty within the last 30 days? | FALSE
60 | SUMCCI | High Cumulative Amount - Inbound - Counterparty (description has to be updated as the rule doesn't look at count but rather on amount) | Significant number of transactions received from a Counterparty over a short period | tx_direction = Inbound AND sum of tx_base_amount per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Inbound transaction? Has the sum of Inbound transactions that this customer has received from a single countearprty within 14 days been greater than a set [Amount]? | FALSE
61 | SUMCCO | High Cumulative Amount - Outbound - Counterparty | Significant number of transactions sent to a Counterparty over a short period | tx_direction = Outbound AND sum of tx_base_amount per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Outbound transaction? Has the sum of Outbound transactions that this customer has sent to a single countearprty within 14 days been greater than a set [Amount]? | TRUE
62 | NUMCCI | High Velocity - Inbound - Counterparty | High number of transactions received from a Counterparty over a short period | tx_direction = Inbound AND count of tx per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Inbound transaction? Has the number of Inbound transactions that this customer has received from a single countearprty within 14 days been greater than a set [Number]? | TRUE
63 | NUMCCO | High Velocity - Outbound - Counterparty | High number of transactions sent to a Counterparty over a short period | tx_direction = Outbound AND count of tx per [customer_id, counterparty_id & tx_direction} in 14 days > [Amount] | Was the transaction an Outbound transaction? Has the number of Outbound transactions that this customer has sent to a single countearprty within 14 days been greater than a set [Number]? | TRUE
Dormant Account
64 | DORMANT | Dormant Account | First activity of client after a long period of dormancy | count of tx per {customer_id} over all-times > 1 AND count of tx per {customer_id} in 180 days = 1 | Has this nt been the customer's first-ever transaction? Has this been the customer's first transactions in the most recent X days (or more, by implication)? | FALSE
Cancellations
65 | NUMCHRG | High Velocity - Chargeback | Significant number of chargebacks over a short period of time | tx_type = [Type] AND count of tx per {customer_id & tx_type} in 14 days > [Number] | Was the transaction of a sepecified transaction type (chargeback)? Has the customer had more than a set [Number] of chargeback transactions within the last 14 days? | FALSE
66 | SUMCHRG | High Cumulative Amount - Chargeback | High sum of chargebacks over a short period of time | tx_tyep = [Type] AND sum of tx_base_amount per {customer_id & tx_type} in 14 days > [Amount] | Was the transaction of a sepecified transaction type (chargeback)? Has the sum of the customer's chargeback transactions within the last 14 days been greater than a set [Amount]? | FALSE
67 | NUMREFND | High Velocity - Refund | Significant number of refunds over a short period of time | tx_tyep = [Type] AND count of tx per {customer_id & tx_type} in 14 days > [Number] | Was the transaction of a sepecified transaction type (refund)? Has the customer had more than a set [Number] of refund transactions within the last 14 days? | FALSE
68 | SUMREFND | High Cumulative Amount - Refund | High sum of refunds over a short period of time | tx_tyep = [Type] AND sum of tx_base_amount per {customer_id & tx_type} in 14 days > [Amount] | Was the transaction of a sepecified transaction type (refund)? Has the sum of the customer's refund transactions within the last 14 days been greater than a set [Amount]? | FALSE
Loans
69 | SETTLE_1 | Early Settlement (rename as there are 2 rules with the same name) (update the description as it doesn't match the rule) | Loan funding followed by a loan settlement within a short time period | tx_type = [Type] AND tx_loan_settlement_datetime - tx_date_time > [Days] | Was the alerted transaction a loan settlement? Was there less than a set number of [Days] between the time of the expected settlement date and the loan settlement? | FALSE
70 | SETTLE_2 | Early Settlement | Loan funding followed by a loan settlement within a short time period | tx_type = [Type] AND customer_loan_amount (Default: 0) ≠ 0 AND tx_base_amount > [Percentage]/100 * customer_loan_amount | Was the alerted transaction a loan payment? Was the customer loan amount available in the transaction data (not 0)? Was the customer's loan payment transaction greater than a set [Percentage] of the customer's loan amount? | FALSE
71 | LRGLOANP | Large Loan Repayments - Instalment Amount (Description should be corrected) | High cumulative loan repayments in amount that exceed expected monthly installment amount | tx_type = [Type] AND customer_expected_installement_amount (Default: 0) ≠ 0 AND tx_base_amount > [Factor] * customer_expected_installement_amount | Was the transaction a loan repayment transaction? Was the customer's loan instalment amount abvailable in the transaction data (not 0)? Was the transaction more than a set [Factor] times greater than the customer's monthy expected loan installment amount? | FALSE
72 | NUMLOAN | High Velocity Loan Repayments | High number of loan repayments within a short time period | tx_type = [Type] AND count of tx per {customer_id & tx_type} in 90d > [Number] | Was the transaction a loan repayment transaction? Has the customer's had more than a set [Number] of loan repayment transactions within the last 90 days? | FALSE
73 | MANYLOAN | Multiple Loans | Multiple new loans taken by the client over a short period | tx_type = [Type] AND unique count of customer_loan_id per {customer_id & tx_type} in 30d > [Number] AND count of tx per {customer_loan_id, customer_id & tx_type} in 30d = 1 | Was the transaction a loan funding transaction? Has the customer had loan funding transactions that have been associated with more than a set [Number] of different loans within 30 days? Was this the customer's first loan fudning transaction for this loan ID within the last 30 days? (A condition that is used to only alert on the first new loan fudning transaction when a new loan ID is used) | FALSE
74 | LOAN>INC | Large Loan Repayments - Monthly Income | High cumulative repayments in amount that exceeds expected client income | tx_type = [Type] AND customer_income (default: 0) ≠ 0 AND sum of tx_base_amount per {customer_id, tx_type, tx_calendar_month & tx_calendar_year} in 31d > [Factor] * customer_income | Was the transaction a loan repayment transaction? Was the customer income field not empty? Has the customer's sum of loan repayment transactions more than a set [Factor] times exceeded the customer's income within the calendar month? (The customer's income is understood as a monthly income) | FALSE
75 | TX>INC | Large Loan Repayments - Monthly Income |  | tx_type = [Type] AND customer_income (default: 0) ≠ 0 AND tx_base_amount > [Factor] * customer_income | Was the transaction a loan repayment transaction? Was the customer income field not empty? Was the customer' loan repayment transaction more than a set [Factor] times greater than the customer's income? (The customer's income is understood as a monthly income) | FALSE
76 | TX>%LOAN | Loan Payment Almost Reaches Loan Balance | Single loan repayment settles a high percentge of the loan balance Outgoing loand repayment transaction of X is greater than limit of Y% of loan balance | tx_type = [Type] AND customer_loan_base_balance (default: 0) ≠ 0 AND tx_base_amount > [Amount] AND tx_base_amount > ([Percentage]/100) * of customer_loan_base_balance | Was the tansaction a loan repayment transaction? Was the customer loan base balance field not empty? Was the transaction greater than a set [Amount]? (condition that is used to eliminate cases from creating an alert, when a transation is more than a set [Percentage] of the custoemr's loan balance, albeit is also of an amount that is deemed insignificant) Was the transaction greater than a set [Percentage] of the customer's loan balance (in base currency)? | FALSE
Cards
77 | SUMCARD | High Sum of Card Transactions | High sum of card transactions - accross all transaction types and directions | tx_type = [Type] AND sum of tx_base_amount per {customer_id & tx_type} in 7d > [Amount] | Was the transaction a card repayment tx? Has the customer sum of card repayment transactions exceeded the set [Amount] within 7 days? | FALSE
78 | NUMRECRD | High Velocity Card Repayments | High number card repayments over a short period | tx_type = [Type] AND count of tx per {customer_id & tx_type} in 7d > [Number] | Was the transaction a card repayment tx? Has the customer sent more than a set [Number] of card repayment transactions within 7 days? | FALSE
79 | SUMRECRD | Large card repayment - Credit Limit | High cumulative card repayments in amount that exceeds credit limit | tx_type = [Type] AND customer_credit_limit (Default: 0) ≠ 0 AND sum of tx_base_amount per {customer_id & tx_type} in 7d > [Factor] * customer_credit_limit (Default: 0) | Was the transaction a card repayment tx? Was the customer's credit limit provided? Has the customer sum of card repayment transactions more than a set [Factor] times exceeded the customer's credit limit within 7 days? | FALSE
80 | TXCARD | Payment limit - card refund | Card refunds are greater than limit | tx_direction = Inbound AND tx_type = [Type] AND tx_base_amount > [Amount] | Was the transaction one that the customer has received (Inbound)? Was the transction type a card refund? Was the card refund greater than a set [Amount]? | FALSE
81 | SUMCRDRF | High Cumulative value of card refunds | Sum of card refunds over a set period is greater than limit | tx_direction = Inbound AND tx_type = [Type] AND sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 30 days > [Amount] | Was the transaction one that the customer has received (Inbound)? Was the transaction a card refund tx? Has the customer sum of Inbound card refund transactions exceeded the set [Amount] within 30 days? | FALSE
82 | NUMCRDRF | High Velocity Card refunds | High number of refunds within a short time period | tx_direction = Inbound AND tx_type = [Type] AND count of tx per {customer_id, tx_direction & tx_type} in 30 days > [Number] | Was the transaction one that the customer has received (Inbound)? Was the transaction a card refund tx? Has the customer received more than a set [Number] of Inbound card refund transactions within 30 days? | FALSE
83 | CREF>SUM | Card refund exceeds payments | Card refund exceeds total value of card payments over 30days rule logic explained: Card refund follows multiple card payments over 30 days, such that the card refund value exceeds the sum of the card payments | tx_type = [Type] AND tx_direction = Inbound AND tx_base_amount > [Amount] AND count of tx per {customer_id} [Filter: tx_type = card_payment, tx_direction = Outbound] in 30 days > [Number] AND tx_base_amount > [Factor] * sum of tx_base_amount per {customer_id} [Filter: tx_type = card_payment AND tx_direction = Outbound] in 30 days | Was the transaction type a card refund? Was the transaction an Inbound tx? Has the customer had made more than a set [Number] of Outbound card payments in the last 30 days? Was the Inbound card refund more than a set [Factor] of times greater than the cusomter's sum of Outbound card payments over the last 30 days? | FALSE
84 | HRCHNNL | Transaction involving high risk payment channels | Card payments via risk channels (Manual card number entry, Signature, non CVV, Invalid AVS check, Offline presentments...) | ll_tx_payment_channel = [Risk] AND tx_base_amount > [Amount] | Was the transaction involving a high-risk payment channel (based on lookup list provided by client)? Was the transaction greater than a set [Amount]? | FALSE
85 | HRMRCHNT | Transaction involving high risk merchant | A card payment to a merchant Category Code that is designated as high risk | ll_tx_mcc_code = [Risk] AND tx_base_amount > [Amount] | Was the transaction involving a high-risk MCC (based on lookup list provided by client)? Was the transaction greater than a set [Amount]? | FALSE
Historical Activity
86 | HSUMATM | High Value - ATM | Total value of ATM transactions exceeds client’s client’s historical average in | tx_type = [Type] AND count of tx per {customer_id, tx_type} over all-time > count of tx per {customer_id, tx_type} in 180 days AND sum of tx_base_amount per {customer_id, tx_type} in 3 days > [Amount] AND sum of tx_base_amount per {customer_id, tx_type} in 3 days > ( [Factor] { [ sum of tx_base_amount per {customer_id, tx_type} in 180 days - sum of tx_base_amount per {customer_id, tx_type} in 3 days) ] / 59 } ) | Was the transaction an ATM tx? Has the customer been active for over a year (Has the customer had at least 1 ATM transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first year of their life cycle) Has the customer's sum of ATM transactions in the last 3 days been greater than a set [Amount]? (A condition that is used to exclude cases when the daily ATM sum is more than a set [Factor] times greater than the historic average daily sum, although of an insignificantly low value) Has the custoemer's sum of ATM transactions in the last 3 days been more than a set [Factor] times greater than the customer's 3-day average ATM transaction value (when the average is caclulated from the 177 days preceding the most recent 3 days)? | FALSE
87 | HNUMATM | High Velocity - ATM | Total number of ATM transactions exceeds client’s historical average | tx_type = [Type] AND count of tx per {customer_id, tx_type} over all-time > count of tx per {customer_id, tx_type} in 180 days AND count of tx per {customer_id, tx_type} in 3 days > [Number] AND count of tx per {customer_id, tx_type} in 3 days > ( [Factor] { [ count of tx per {customer_id, tx_type} in 180 days - count of tx per {customer_id, tx_type} in 3 days) ] / 59 } ) | Was the transaction an ATM tx? Has the customer been active for over a year (Has the customer had at least 1 ATM transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first year of their life cycle) Has the customer's had more than a set [Number] of ATM transactions within the last 3 days? (A condition that is used to exclude cases when within 3 day, a customer's number of ATM is more than a set [Factor] times greater than the historic average daily number, although of an insignificantly low value) Has the customer had more than a set [Factor] times more ATM transactions within the last 3 days than their historic 3-day average number pf ATM transactions (when the average is caclulated from the 180 days preceding the most recent 3 days)? | FALSE
88 | HASUMI | High Cumulative Amount - Historic Average - Inbound | Total value of incoming payments exceeds client’s historical average | tx_direction = Inbound AND count of tx per {customer_id & tx_direction} over all-time > count of tx per {customer_id & tx_direction} in 180 days AND sum of tx_base_amount per {customer_id & tx_direction} in 3 days > [Amount] AND sum of tx_base_amount per {customer_id & tx_direction} in 3 days > ( [Factor] { [ sum of tx_base_amount per {customer_id & tx_direction} in 180 days - sum of tx_base_amount per {customer_id & tx_direction} in 3 days) ] / 59 } ) | Was the transaction an Inbound transaction? Has the customer been active for over 180 days (Has the customer had at least 1 Inbound transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's sum of Inbound transactions in 3 days been greater than a set [Amount]? (A condition that is used to exclude cases when the 3-day Inbound sum is more than a set [Factor] times greater than the cusotmer's 3-day historic average Inbound sum, although of an insignificantly low value) Has the customer's sum of Inbound transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average sum of Inbound transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
89 | HANUMI | High Velocity - Historic Average - Inbound | Total number of incoming transactions exceeds client’s historical average | tx_direction = Inbound AND count of tx per {customer_id & tx_direction} over all-time > count of tx per {customer_id, tx_direction} in 180 days AND count of tx per {customer_id & tx_direction} in 3 days > [Number] AND count of tx per {customer_id & tx_direction} in 3 days > ( [Factor] { [ count of tx per {customer_id & tx_direction} in 180 days - count of tx per {customer_id & tx_direction} in 3 days) ] / 59 } ) | Was the transaction an Inbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Inbound transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer had more than a set [Number] of Inbound transctions within the last 3 days? (A condition that is used to exclude cases when the number of Inbound transactions in 3 days is more than a set [Factor] times greater than the customer's 3-day historic average number of Inbound transactions, although of an insignificantly low number) Has the customer's number of Inbound transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average number of Inbound transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
90 | HASUMO | High Cumulative Amount - Historic Average - Outbound | Total value of outgoing transactions exceeds client’s historical average | tx_direction = Outbound AND count of tx per {customer_id & tx_direction} over all-time > count of tx per {customer_id & tx_direction} in 180 days AND sum of tx_base_amount per {customer_id & tx_direction} in 3 days > [Amount] AND sum of tx_base_amount per {customer_id & tx_direction} in 3 days > ( [Factor] { [ sum of tx_base_amount per {customer_id & tx_direction} in 180 days - sum of tx_base_amount per {customer_id & tx_direction} in 3 days) ] / 59 } ) | Was the transaction an Inbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Inbound transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's sum of Inbound transactions in 3 days been greater than a set [Amount]? (A condition that is used to exclude cases when the 3-day Inbound sum is more than a set [Factor] times greater than the customer's 3-day historic average Inbound sum, although of an insignificantly low value) Has the customer's sum of Inbound transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average sum of Inbound transactions (when the average is caclulated from the 177days preceding the evaluated 3 days)? | FALSE
91 | HANUMO | High Velocity - Historic Average - Outbound | Total number of outgoing transactions exceeds client’s historical average | tx_direction = Outbound AND count of tx per {customer_id & tx_direction} over all-time > count of tx per {customer_id & tx_direction} in 180 days AND count of tx per {customer_id & tx_direction} in 3 days > [Number] AND count of tx per {customer_id & tx_direction} in 3 days > ( [Factor] { [ count of tx per {customer_id & x_direction} in 180 days - count of tx per {customer_id & tx_direction} in 3 days) ] / 59 } ) | Was the transaction an Outbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Inbound transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer had more than a set [Number] of Inbound transctions within the last 3 days? (A condition that is used to exclude cases when the number of Inbound transactions in 3 days is more than a set [Factor] times greater than the customer's 3-day historic average number of Inbound ATM transactions, although of an insignificantly low number) Has the customer's number of Inbound transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average number of Inbound transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
92 | HCSHSUMI | High Cumulative Amount Cash - Historic Average - Inbound | Total value of cash deposits exceeds client’s historical average | tx_type = [Type] AND tx_direction = Inbound AND count of tx per {customer_id, tx_direction & tx_type} over all-time > count of tx per {customer_id, tx_direction & tx_type} in 180 days AND sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days > [Amount] AND sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days > ( [Factor] { [ sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 180 days - sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days) ] / 59 } ) | Was the transaction an cash tx? Was the transaction an Inbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Inbound cash transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's sum of Inbound cash transactions in 3 days been greater than a set [Amount]? (A condition that is used to exclude cases when the 3-day cash sum is more than a set [Factor] times greater than the 3-day historic average sum, although of an insignificantly low value) Has the customer's sum of cash transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average sum of cash transaction value (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
93 | HCSHNUMI | High Velocity Cash - Historic Average - Inbound | Total number of cash deposits exceeds client’s historical average | tx_type = [Type] AND tx_direction = Inbound AND count of tx per {customer_id, tx_direction & tx_type} over all-time > count of tx per {customer_id, tx_direction & tx_type} in 180 days AND count of tx per {customer_id, tx_direction & tx_type} in 3 days > [Number] AND count of tx per {customer_id, tx_direction & tx_type} in 3 days > ( [Factor] { [ count of tx per {customer_id, tx_direction & tx_type} in 180 days - count of tx per {customer_id, tx_direction & tx_type} in 3 days) ] / 59 } ) | Was the transaction an cash tx? Was the transaction an Inbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Inbound cash transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer had more than a set [Number] of Inbound cash transctions within the last 3 days? (A condition that is used to exclude cases when the number of Inbound cash transactions in 3 days is more than a set [Factor] times greater than the 3-day historic average number of Inbound cash transactions, although of an insignificantly low number) Has the customer's number of Inbound cash transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average number of Inbound cash transactions (when the average is caclulated from the 177days preceding the evaluated 3 days)? | FALSE
94 | HCSHSUMO | High Cumulative Amount Cash - Historic Average - Outbound | Total value of cash withdrawals exceeds client’s historical average | tx_type = [Type] AND tx_direction = Outbound AND count of tx per {customer_id, tx_direction & tx_type} over all-time > count of tx per {customer_id, tx_direction & tx_type} in 180 days AND sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days > [Amount] AND sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days > ( [Factor] { [ sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 180 days - sum of tx_base_amount per {customer_id, tx_direction & tx_type} in 3 days) ] / 59 } ) | Was the transaction an cash tx? Was the transaction an Outbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Outbound cash transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's sum of Outbound cash transactions in 3 days been greater than a set [Amount]? (A condition that is used to exclude cases when the 3-day cash sum is more than a set [Factor] times greater than the 3-day historic average Outbound sum, although of an insignificantly low value) Has the customer's sum of Outbound cash transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average sum of Outbound cash transaction value (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
95 | HCSHNUMO | High Velocity cash - Historic Average - Outbound | Total number of cash withdrawals exceeds client’s historical average | tx_type = [Type] AND tx_direction = Outbound AND count of tx per {customer_id, tx_direction & tx_type} over all-time > count of tx per {customer_id, tx_direction & tx_type} in 180 days AND count of tx per {customer_id, tx_direction & tx_type} in 3 days > [Number] AND count of tx per {customer_id, tx_direction & tx_type} in 3 days > ( [Factor] { [ count of tx per {customer_id, tx_direction & tx_type} in 180 days - count of tx per {customer_id, tx_direction & tx_type} in 3 days) ] / 59 } ) | Was the transaction an cash tx? Was the transaction an Outbound transaction? Has the customer been active for over a 180 days (Has the customer had at least 1 Outbound cash transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer had more than a set [Number] of Outbound cash transctions within the last 3 days? (A condition that is used to exclude cases when the number of Outbound cash transactions in 3 days is more than a set [Factor] times greater than the 3-day historic average number of Outbound cash transactions, although of an insignificantly low number) Has the customer's number of Outbound cash transactions in 3 days been more than a set [Factor] times greater than the customer's 3-day average number of Outbound cash transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
96 | IN>AVG | Transaction Limit - Historic Average - Inbound | Inbound transaction exceeds client’s historical average | tx_direction = Inbound AND tx_base_amount > [Amount] AND count of transactions per {customer_id & tx_direction} (excl) over all-time > [Number] AND tx_base_amount > average tx_base_amount per{customer_id & tx_direction} over all-time (excl) * [Factor]} | Was the transaction an Inbound tx? Was the tx greater than a set [Amount]? ( A condition used to exclude cases whena tx is more than a set [Factor] times greater than the average, but it is of an insignificant value) Has the customer had more than a set [Number] of previous Inbound transactions over all-time? (A condition that is used to ensure that the average is consisted of at least a set [Number] of previous Inbound transactions) Was the Inbound transaction more than a set [Factor] times greater than the cusotmer's average Inbound transaction value over the customer's client life cycle? (The calculated average excludes the evaluated transaction) | FALSE
97 | OUT>AVG | Transaction Limit - Historic Average - Outbound | Outbound transaction exceeds client’s historical average | tx_direction = Outbound AND tx_base_amount > [Amount] AND count of transactions per {customer_id & tx_direction} (excl) over all-time > [Number] AND tx_base_amount > average tx_base_amount per{customer_id & tx_direction} over all-time (excl) * [Factor]} | Was the transaction an Outbound tx? Was the tx greater than a set [Amount]? ( A condition used to exclude cases whena tx is more than a set [Factor] times greater than the average, but it is of an insignificant value) Has the customer had more than a set [Number] of previous Inbound transactions over all-time? (A condition that is used to ensure that the average is consisted of at least a set [Number] of previous Inbound transactions) Was the Inbound transaction more than a set [Factor] times greater than the cusotmer's average Inbound transaction value over the customer's client life cycle? (The calculated average excludes the evaluated transaction) | FALSE
98 | SAFE>HA | High Velocity Safe Custody Account Usage - Historic Average | Total number of Safe Custody account usage exceeds client’s historical average | tx_type = [Type] AND count of tx per {customer_id, tx_type } over all-time > count of tx per {customer_id, tx_type} in 180 days AND count of tx per {customer_id, tx_type } in 3 days > [Number] AND count of tx per {customer_id, tx_type } in 3 days > ( [Factor] { [ count of tx per {customer_id, tx_type } in 180 days - count of tx per {customer_id, tx_type } in 3 days) ] / 59 } ) | Was the transaction a safe custody account type tx? Has the customer been active for over 180 days (Has the customer had at least 1 safe custody account type transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's had more than a set [Number] of safe custody customer account type transactions within the last 3 days? (A condition that is used to exclude cases when within 3 days, a customer's number of safe custody customer account type transactions is more than a set [Factor] times greater than the customer's historic 3-day average number, although of an insignificantly low value) Has the customer had more than a set [Factor] times more safe custody customer account type transactions within the the last 3 days than their historic 3-day average number of safe custody customer account type transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
99 | PREPC>HA | High Velocity Historic Average - Prepaid Card | Total number of prepaid card purchase/top up exceeds client's historical average | tx_type = [Type] AND count of tx per {customer_id, tx_type } over all-time > count of tx per {customer_id, tx_type} in 180 days AND count of tx per {customer_id, tx_type } in 3 days > [Number] AND count of tx per {customer_id, tx_type } in 3 days > ( [Factor] { [ count of tx per {customer_id, tx_type } in 180 days - count of tx per {customer_id, tx_type } in 3 days) ] / 59 } ) | Was the transaction a prepaid card tx? Has the customer been active for over 180 days (Has the customer had at least 1 prepaid card transactions more than 180 days ago)? (A condition that is used to ensure that we are calculating an average from an available representative sample of data - this condition would cause the rule not to alert in the customer's first 180 days of their life cycle) Has the customer's had more than a set [Number] of prepaid card transactions within the last 3 days? (A condition that is used to exclude cases when within 3 days, a customer's number of prepaid card transactions is more than a set [Factor] times greater than the customer's historic 3-day average number, although of an insignificantly low value) Has the customer had more than a set [Factor] times more prepaid card transactions within the the last 3 days than their historic 3-day average number of prepaid card transactions (when the average is caclulated from the 177 days preceding the evaluated 3 days)? | FALSE
Non-transactional activity
100 | CDC01 | Multiple Detail Change | Significant number of client personal detail (address, zip, name…) changes Rule logic explained: Compare a specific client field (e.g. zip code) and alert if it was changed more than X times over a set period | unique count of customer_postcode per {customer_id} in 180 days > [Number] AND count of tx per {customer_postcode & customer} in 180 days = 1 | Has the customer had transactions with more han a set [Number] of different post codes over 180 days? Has this been a transaction when the customer used a new post code? | FALSE
Peer Group
101 | PGAV-IN | Peer Group Average - Inbound | An Inbound transaction's value was over the peer group average of the last 7d | tx_direction = Inbound AND tx_base_amount > [Amount] AND customer_type = [Type] AND tx_base_amount > average of base_amount per {tx_direction & customer_type} in 7 days (excl) * [Factor] AND count of tx per {tx_direction & customer_type} in 7 days (excl) > [Number] | Was the transactions an Inbound transaction? Was the transaction created than a set [Amount]? Was the transaction more than a set [Factor] times greater than the average Inbound transaction value of the same customer type within the last 7 days? (The calulated average excludes the evaluated transaction) Has the peer group had at least a set [Number] of previous Inbound transactions within the evluated 7 days? | FALSE
102 | PGAV-OUT | Peer Group Average - Outbound | An Outbound transaction's value was over the peer group average of the last 7d | tx_direction = Outbound AND tx_base_amount > [Amount] AND customer_type = [Type] AND base_amount > average of base_amount per {tx_direction & customer_type} in 7 days (excl) * [Factor] AND count of tx per {tx_direction & customer_type} in 7 days (excl) > [Number] | Was the transactions an Outboundtransaction? Was the transaction created than a set [Amount]? Was the transaction more than a set [Factor] times greater than the average Outbound transaction value of the same customer type within the last 7 days? (The calulated average excludes the evaluated transaction) Has the peer group had at least a set [Number] of previous Outbound transactions within the evluated 7 days? | FALSE
Screening
103 | CTPYSANC | Counterparty Sanctions Screening | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND counterparty entity has matched against one or more entities from the selected sanction lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty match against one or more entities from the selected sanction lists? | FALSE
104 | CTPYWARN | Counterparty Warnings Screening Descriptipon - update desc to reflect this is Warning | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND counterparty entity has matched against one or more entities from the selected warning lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty match against one or more entities from the selected warning lists? | FALSE
105 | CTPYFITP | Counterparty Fitness & Probity Screening | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND counterparty entity has matched against one or more entities from the selected fitness & probity lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty match against one or more entities from the selected fitness & probity lists? | FALSE
106 | CUSTSANC | Customer Sanctions Screening | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND customer entity has matched against one or more entities from the selected lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the customer match against one or more entities from the selected lists? | FALSE
107 | CUSTWARN | Customer Warnings Screening | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND customer entity has matched against one or more entities from the selected warning lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the customer match against one or more entities from the selected warning lists? | FALSE
108 | CUSTFITP | Customer Fitness & Probity Screening | Screening of Entity name against sanction lists. (e.g Beneficiary, etc). | tx_type is not in list [Type] AND customer entity has matched against one or more entities from the selected fitness & probity lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the customer match against one or more entities from the selected fitness & probity lists? | FALSE
109 | INSTSANC | Institution Sanction Screening | Screening of Institution/ Company names against sanction lists. | tx_type is not in list [Type] AND the counterparty Institution entity has matched against one or more entities from the selected lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty institution match against one or more entities from the selected lists? | FALSE
110 | INSTWARN | Institution Warnings Screening |  | tx_type is not in list [Type] AND the counterparty institution entity has matched against one or more entities from the selected fitness & probity lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty institution match against one or more entities from the selected fitness & probity lists? | FALSE
111 | INSTFITP | Institution Fitness & Probity Screening |  | tx_type is not in list [Type] AND the counterparty institution entity has matched against one or more entities from the selected lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the counteraprty institution match against one or more entities from the selected lists? | FALSE
112 | REFTEXT | Reference Text Entity Screening | Screening of entities within the transaction reference text | tx_type is not in list [Type] AND tx_reference_text contained a match against one or more entities from the selected sanction lists, using the specified screening conditions and fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the reference text contain a sanction match? | FALSE
113 | RISKWORD | Risk Words Reference Text | Screening of risk words within the transaction reference text | tx_type is not in list [Type] AND tx_reference_text contained a match against one or more items from the selected risk word list(s), using the specified fuzziness | Was the transaction type other than what was specified in the [Type] list? (A condition used to exclude given transaction types that are not desirable to be screened.) Did the reference text contain a a match againt one or more items from any of the selected risk word list(s)? | FALSE